## Initial Plan
Color Coding |  |  | Completed |  |  |  | SPRING 2023 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | Date | 2023-01-24 | 2023-01-31 | 2023-02-07 | 2023-02-14 | 2023-02-21 | 2023-02-28 | 2023-03-07 | 2023-03-21 | 2023-03-28 | 2023-04-11 | 2023-04-18 | 2023-04-25 | 2023-05-02 | 2023-05-09
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | All | 2023-01-24 | 2023-01-26 | 100%
| Confirm Project Team Roles |  | All | 2023-01-24 | 2023-01-26 | 100%
| Develop two business cases |  | Sai Teja | 2023-01-24 | 2023-01-29 | 100%
| Develop Project Initiation Document (PID) |  | Sai Teja | 2023-01-31 | 2023-02-05 | 100%
| Produce initial Project Plan, RACI |  | Sai Teja | 2023-02-07 | 2023-02-12 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Amala, Bhakti | 2023-02-14 | 2023-02-19 | 100%
| Produce Context Diagram, Define System Interfaces |  | Rushda Tahera | 2023-02-14 | 2023-02-19 | 100%
| Agree to System Requirements types |  | Manish, Nidhi | 2023-02-14 | 2023-02-19 | 100%
| Compile List of Customer Needs |  | Sai Teja, Jahid | 2023-02-14 | 2023-02-19 | 100%
| Define Product Requirement type |  | All | 2023-02-21 | 2023-02-26 | 100%
| Define Stakeholders Requirements type |  | All | 2023-02-21 | 2023-02-26 | 100%
| Define Business Requirements |  | Sai Teja, Rushda | 2023-02-21 | 2023-02-26 | 100%
| Define Functional Decomposition |  | Amala, Bhakti | 2023-02-21 | 2023-02-26 | 100%
| Produce RCT document |  | All | 2023-02-21 | 2023-02-26 | 100%
| Decide which features to implement this semester |  | All | 2023-02-21 | 2023-02-26 | 100%
| Produce analysis diagrams (UML, DFD) |  | Tahera, Amala, Bhakti | 2023-02-28 | 2023-03-05 | 0%
| Define functional requirements (User Stories) |  | Sai Teja | 2023-02-28 | 2023-03-05 | 0%
| Update Project Plan with additional requirements tasks |  | Rushda | 2023-02-28 | 2023-03-05 | 0%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) |  | TBD | 2023-04-04 | 2023-04-09 | 0%
| Database Design (ERD, Table spec) |  | TBD | 2023-03-21 | 2023-03-26 | 0%
| System Interface Design |  | TBD | 2023-03-21 | 2023-03-26 | 0%
| User interface design |  | TBD | 2023-02-14 | 2023-04-10 | 0%
MILESTONE 3: DESIGN COMPLETED
Code | Create Account | GUI & Functionality Design | Nidhi, Sai Teja | 2023-03-02 | 2023-04-21 | 50%
|  | Coding | Tahera, Sai Manish | 2023-03-02 | 2023-04-21 | 50%
| Authenicate Account | GUI & Functionality Design | Amala, Bhakti | 2023-03-02 | 2023-04-21 | 50%
|  | Coding | Rushda, Jahid | 2023-03-02 | 2023-04-21 | 50%
| Update Account | GUI & Functionality Design | TBD | 2023-03-07 | 2023-04-21 | 0%
|  | Coding | TBD | 2023-03-07 | 2023-04-21 | 0%
| Maintan Account Summary | GUI & Functionality Design | TBD | 2023-03-07 | 2023-04-21 | 0%
|  | Coding | TBD | 2023-03-07 | 2023-04-21 | 0%
| Close Account | GUI & Functionality Design | TBD | 2023-03-07 | 2023-04-21 | 0%
|  | Coding | TBD | 2023-03-07 | 2023-04-21 | 0%
MILESTONE 4: CODING COMPLETED
Testing | Plan testing, produce a Test Plan document |  | TBD | 2023-04-11 | 2018-04-30 | 0%
| Evaluate Features to be Tested |  | TBD | 2023-04-11 | 2018-04-30 | 0%
| Create Account | Design Test Cases | TBD | 2023-04-11 | 2018-04-30 | 0%
|  | Execute Test Cases | TBD | 2023-04-11 | 2018-04-30 | 0%
|  | Anaylze Test Results | TBD | 2023-04-11 | 2018-04-30 | 0%
| Authenicate Account | Design Test Cases | TBD | 2023-04-11 | 2018-04-30 | 0%
|  | Execute Test Cases | TBD | 2023-04-11 | 2018-04-30 | 0%
|  | Anaylze Test Results | TBD | 2023-04-11 | 2018-04-30 | 0%
| Update Account | Design Test Cases | TBD | 2023-04-22 | 2018-04-30 | 0%
|  | Execute Test Cases | TBD | 2023-04-22 | 2018-04-30 | 0%
|  | Anaylze Test Results | TBD | 2023-04-22 | 2018-04-30 | 0%
| Maintan Account Summary | Design Test Cases | TBD | 2023-04-22 | 2018-04-30 | 0%
|  | Execute Test Cases | TBD | 2023-04-22 | 2018-04-30 | 0%
|  | Anaylze Test Results | TBD | 2023-04-22 | 2018-04-30 | 0%
| Close Account | Design Test Cases | TBD | 2023-04-22 | 2018-04-30 | 0%
|  | Execute Test Cases | TBD | 2023-04-22 | 2018-04-30 | 0%
|  | Anaylze Test Results | TBD | 2023-04-22 | 2018-04-30 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2023-05-02 | 2023-05-09 | 0%